## Framework &W (hidden)
13
Programme of action |  | Objectives |  | Activity | Sub-activity |  | Timeframe | Costs | Mitigation | Adaptation | Feasibility | NDC | Within WASAC mandate | Existing processes/ strategies | Lead agency/ department/ line ministery | Other key partners | Adresses vulnerability | Remarks
2.1 | Low carbon and SMART infrastructure and services
Low carbon
Greenhouse gas reduction opportunities (co-benefits)
|  |  | 1 | Strengthen ongoing NRW initiatives by reducing physical losses
[5 empty] | 1.1 | Estimate current GHG emmissions of WASAC and potential gains | Short | Low | ✔️
[5 empty] | 1.2 | Identify existing utilities with high NRW related to climate hazards | Short | Low | ✔️
[5 empty] | 1.3 | Replacement of pipes in selected utilities | Medium | High | ✔️
|  |  | 2 | Increase energy efficieny by installing high efficient pumps and other energy saving technologies
[5 empty] | 2.1 | Replace all pumps with high energy efficient pumps | Medium | Low | ✔️
[5 empty] | 2.2 | Replace all remaining diesel generator pumps with grid or solar | Medium | Medium | ✔️
[5 empty] | 2.3 | Apply energy saving processes throughout production | Medium | Low | ✔️
Resilient SMART Infrastructure
Infrastructures able to cope and respond even during extreme weather events
|  |  | 3 | Developing and implementing a risk-based asset management system. | [12 empty] | Infrastrcuture failure
[5 empty] | 3.1 | Develop training material and train key colleagues | Short | Low |  | ✔️
[5 empty] | 3.2 | Adapt asset categories to reflect risks | Short | Low |  | ✔️
|  |  | 4 | Revising design norms and standards | [12 empty] | Infrastrcuture failure
[5 empty] | 4.1 | Identify infrastructure most at risk and their needed adaptation | Short | Low |  | ✔️
[5 empty] | 4.2 | Enhanced supervision in areas that are more disaster prone | Medium | Low |  | ✔️
|  |  | 5 | Reducing Water demand by using water saving devices | [7 empty] | ✔️ |  |  |  |  | drought
[5 empty] | 5.1 | Engage with private sector to offer water saving devices to consumers | Short | Low |  | ✔️
[5 empty] | 5.2 | Scale water component green city iniciative | Long | High |  | ✔️
|  |  | 6 | Protection of priority assets (intake structures, pumping stations and conveyance pipes) against climate hazards | [12 empty] | Infrastrcuture failure
[5 empty] | 6.1 | Based on risk assesment, create detailed plan | Short | Low |  | ✔️
[5 empty] | 6.2 | Implement plan (e.g. shifting locations of intakes and pumping stations) | Long | High |  | ✔️
[5 empty] | 6.3 | All weather access to assets such as landfills, waste water treatment plants | Medium | Medium |  | ✔️
Reslient services
Services able to cope and respond even during extreme weather events
|  |  | 7 | Sanitation and sewers | [7 empty] | ✔️
[5 empty] | 7.1 | Avoid storm water entry into sewerage | Long | High |  | ✔️
[5 empty] | 7.2 | Weatherproof latrines against extreme weather events | Medium | Medium |  | ✔️
|  |  | 8 | Using real-time monitoring of weather and water resources data during expected (extreme?) weather events | [7 empty] | ✔️ |  |  |  |  | Infrastrcuture failure
[5 empty] | 8.1 | Create action protocol based on weather warnings | Short | Medium |  | ✔️
[5 empty] | 8.2 | Monitor systems behaviour during extreme events | Medium | Medium |  | ✔️
|  |  | 9 | Contingency plans for disasters | [12 empty] | Infrastrcuture failure
[5 empty] | 9.1 | Define protocol on recording disaster events (via WASH Cluster) | Short | Low |  | ✔️
[5 empty] | 9.2 | Create financial mechanism for disaster recovery | Medium | High |  | ✔️
[5 empty] | 9.3 | Create disaster management protocols at utility levels | Medium | Medium |  | ✔️
[5 empty] | 9.4 | Create redundancy in sources and systems | Long | High |  | ✔️
3.2 | Integrated Water resources management
|  | Pro-active water source management | [14 empty] | drought
With active monitoring and engagement with IWRM partners
|  |  | 10 | Participate in and contribute to catchment protection programmes and projects. | [7 empty] | ✔️
[5 empty] | 10.1 | In high turbidity areas enhance riverbed protection and erosion measurements | Medium | Medium | ✔️ | ✔️
10.2
|  |  | 11 | Water safety planning | [7 empty] | ✔️ |  |  |  |  | water quality
[5 empty] | 11.1 | Hazard and risk assessment | Short | Low |  | ✔️
[5 empty] | 11.2 | Planning and executing improvements | Long | High |  | ✔️
[5 empty] | 11.3 | Monitoring for control measures | Long | Low |  | ✔️
|  |  | 12 | Pro-active monitoring of sources, particular springs | [7 empty] | ✔️ |  |  |  |  | drought
[5 empty] | 12.1 | Analysis of trends in water resources availability for critical intake points | Short | Low |  | ✔️
[5 empty] | 12.2 | Create national spring monitor system | Medium | Medium |  | ✔️
4.2 | Green and climate resilient rural setllements
Rural communities thrive with appropriate technologies and services settlements
With active monitoring and engagement with IWRM partners
|  |  | 13 | Assess and develop appropriate water treatment facilities for settlements | [12 empty] | drought
[5 empty] | 13.1 | Risk categorisation of rural water infrastructures | Medium | Low |  | ✔️
[5 empty] | 13.2 | Enhance protection zones around springs and boreholes | Medium | Medium |  | ✔️
[5 empty] | 13.3 | Explore alternative options such as water kiosks | Medium | Medium |  | ✔️

## Framework
13
| Objectives |  | Strategy area | Activity groups |  | Mitigation | Adaptation | Timeframe | Costs | Feasibility
Low carbon and SMART infrastructure and services
Low carbon
Greenhouse gas reduction opportunities (co-benefits)
|  | 1 | Strengthening ongoing NRW initiatives to reduce physical losses
|  |  |  | 1.1 | Planning and executing improvements in NRW | ✔️ |  | Short | Low | Very feasible
|  |  |  | 1.2 | Estimate current GHG emissions of WASAC and potential gains | ✔️ |  | Short | Low | Feasible
|  |  |  | 1.3 | Identify existing schemes with high NRW related to climate hazards | ✔️ |  | Short | Low | Very feasible
|  |  |  | 1.4 | Replacement of aged pipes (and any other network component) in selected schemes | ✔️ |  | Medium | High | Less feasibility
|  |  |  | 1.5 | Network sectioning and introduction of SMART system monitoring | ✔️ |  | Long | High | Less feasibility
|  | 2 | Increasing energy efficiency by installing high efficient pumps and other energy saving technologies
|  |  |  | 2.1 | Energy audit followed by replace all pumps with high energy efficient pumps | ✔️ |  | Medium | Medium | Very feasible
|  |  |  | 2.2 | Replace all remaining diesel generator pumps with grid or solar | ✔️ |  | Medium | Medium | Very feasible
|  |  |  | 2.3 | Create organisation wide energy saving ethos and apply energy saving processes throughout production | ✔️ |  | Medium | Low | Feasible
|  |  |  | 2.4 | Communication and awareness raising campaigns to reduce water demand and enhance community resilience |  | ✔️ | Short | Low | Very feasible
Resilient SMART Infrastructure
Infrastructures able to cope and respond even during extreme weather events
|  | 3 | Developing and implementing a risk-based asset management system. |  |  |  | ✔️ | Short | Low | Feasible
|  |  |  | 3.1 | Develop training material and train key colleagues |  | ✔️ | Short | Low | Feasible
|  |  |  | 3.2 | Adapt asset categories to reflect risks |  | ✔️ | Short | Low | Feasible
|  |  |  | 3.3 | Improve performance monitoring of assets |  | ✔️ | Short | Medium | Feasible
|  |  |  | 3.4 | Develop a strategic infrastructure plan |  | ✔️ | Medium | Low | Feasible
|  | 4 | Adapting designs and norms to inclue climate change |  |  |  | ✔️ | Medium | Medium | Feasible
|  |  |  | 4.1 | Revise design norms and standards |  | ✔️ | Medium | Medium | Feasible
|  |  |  | 4.2 | Identify infrastructure most at risk and their needed adaptation |  | ✔️ | Short | Low | Feasible
|  |  |  | 4.3 | Enhanced supervision in areas that are more disaster prone |  | ✔️ | Medium | Low | Feasible
|  | 5 | Reducing Water demand by using water saving devices
|  |  |  | 5.1 | Engage with private sector to offer water saving devices to consumers | ✔️ | ✔️ | Short | Low | Very feasible
|  |  |  | 5.2 | Scale water component green city initiative | ✔️ | ✔️ | Long | High | Feasible
|  | 6 | Protecting priority assets (intake structures, pumping stations and conveyance pipes) against climate hazards
|  |  |  | 6.1 | Based on (climate) vulnerability assessment create a detailed plan |  | ✔️ | Short | Low | Very feasible
|  |  |  | 6.2 | Implement detailed plan (e.g. shifting locations of intakes and pumping stations) |  | ✔️ | Long | High | Feasible
|  |  |  | 6.3 | All weather access to assets such as landfills, wastewater treatment plants |  | ✔️ | Medium | Medium | Feasible
Resilient services
Services able to cope and respond even during extreme weather events
|  | 7 | Securing Sanitation and sewers to cope with floods and landslides
|  |  |  | 7.1 | Avoid storm water entry into sewerage |  | ✔️ | Long | High | Less feasibility
|  |  |  | 7.2 | Weatherproof latrines against extreme weather events |  | ✔️ | Medium | Medium | Feasible
|  | 8 | Using real-time monitoring of weather and water resources data during extreme weather events
|  |  |  | 8.1 | Create action protocol based on weather warnings |  | ✔️ | Short | Medium | Very feasible
|  |  |  | 8.2 | Monitor systems behaviour during extreme events |  | ✔️ | Medium | Medium | Feasible
|  |  |  | 8.3 | Post- extreme event assessment |  | ✔️ | Medium | Medium | Feasible
|  | 9 | Implementing contingency plans for disasters
|  |  |  | 9.1 | Define protocol on recording disaster events (via WASH Cluster) |  | ✔️ | Short | Low | Very feasible
|  |  |  | 9.2 | Create financial mechanism for disaster recovery |  | ✔️ | Medium | High | Less feasibility
|  |  |  | 9.3 | Create disaster management protocols at utility level |  | ✔️ | Medium | Medium | Very feasible
|  |  |  | 9.4 | Create redundancy in sources and systems |  | ✔️ | Long | High | Feasible
Integrated Water resources management
Pro-active water source management
With active monitoring and engagement with IWRM partners
|  | 10 | Participating in and contributing to catchment protection programmes and projects.
|  |  |  | 10.1 | Hire and train stakeholder managers |  | ✔️ | Short | Medium | Feasible
|  |  |  | 10.2 | Formulate and implement a company-wide stakeholder management vision and strategy |  | ✔️ | Short | Low | Feasible
|  |  |  | 10.3 | Strengthen the existing catchment management committees and participate in water resource allocation |  | ✔️ | Medium | Medium | Feasible
|  |  |  | 10.4 | In high turbidity areas enhance riverbed protection and erosion measurements | ✔️ | ✔️ | Medium | Medium | Feasible
|  | 11 | Embedding Water safety planning as integral part of source and system management |  |  |  | ✔️
|  |  |  | 11.1 | Assemble water safety plan teams and describe the water supply systems |  | ✔️ | Short | Low | Very feasible
|  |  |  | 11.2 | Hazard and risk assessment |  | ✔️ | Short | Low | Very feasible
|  |  |  | 11.3 | Planning and executing improvements |  | ✔️ | Medium | Low | Feasible
|  |  |  | 11.4 | Monitoring for control measures |  | ✔️ | Medium | Low | Feasible
|  |  |  | 11.5 | Periodic review of the water safety plan |  | ✔️ | Short | Low | Very feasible
|  | 12 | Pro-active monitoring of sources, in particular springs
|  |  |  | 12.1 | Analysis of trends in water resources availability for critical intake points |  | ✔️ | Short | Low | Very feasible
|  |  |  | 12.2 | Create national spring monitor system |  | ✔️ | Medium | Medium | Very feasible
Green and climate resilient rural settlements
Rural communities thrive with appropriate technologies and services settlements
With active monitoring and engagement with IWRM partners
|  | 13 | Assessing and developing appropriate safe water supply facilities for rural settlements
|  |  |  | 13.1 | Risk categorisation of rural water infrastructures, also in design phase |  | ✔️ | Short | Low | Very feasible
|  |  |  | 13.2 | Enhance protection zones around springs and boreholes in water catchment areas |  | ✔️ | Medium | Medium | Very feasible
|  |  |  | 13.3 | Explore alternative options such as water kiosks |  | ✔️ | Medium | Medium | Feasible
|  |  |  | 13.4 | Communication and awareness raising campaigns to enhance community resilience |  | ✔️ | Medium | Low | Very feasible

## Sheet2 (hidden)
1 | Strengthening ongoing NRW initiatives to reduce physical losses | #REF!
2 | Increasing energy efficiency by installing high efficient pumps and other energy saving technologies | #REF!
3 | Developing and implementing a risk-based asset management system. | #REF!
4 | Adapting designs and norms to inclue climate change | #REF!
5 | Reducing Water demand by using water saving devices | #REF!
6 | Protecting priority assets (intake structures, pumping stations and conveyance pipes) against climate hazards | #REF!
7 | Securing Sanitation and sewers to cope with floods and landslides | #REF!
8 | Using real-time monitoring of weather and water resources data during extreme weather events | #REF!
9 | Implementing contingency plans for disasters | #REF!
10 | Participating in and contributing to catchment protection programmes and projects. | #REF!
11 | Embedding Water safety planning as integral part of source and system management | #REF!
12 | Pro-active monitoring of sources, in particular springs | #REF!
13 | Assessing and developing appropriate safe water supply facilities for rural settlements | #REF!
| Action | Vulnerability
| Developing and implementing a risk-based asset management system. | Resilient infrastructure
| Revising design norms and standards | Resilient infrastructure
| Protection of priority assets (intake structures, pumping stations and conveyance pipes) against climate hazards | Resilient infrastructure
| Sanitation and sewers | Resilient infrastructure
| Contingency plans for disasters | Resilient infrastructure
| Using real-time monitoring of weather and water resources data during expected (extreme?) weather events | Water quality
| Participate in and contribute to catchment protection programmes and projects. | Water quality
| Assess and develop appropriate water treatment facilities for settlements | Water quality
| Strengthen ongoing NRW initiatives by reducing physical losses | Water quantity
| Reducing Water demand by using water saving devices | Water quantity
| Water safety planning | Water quantity
| Pro-active monitoring of sources, particular springs | Water quantity

## lookup (hidden)
| Definition | Category | Explanation | Resources
Programme of action | Following the Green growth strategy, these are the programmes of action allocated to WASAC
Objectives
Activity
Sub-activity
Mitigation | Tick if it adresses climate mitigation considerably
Adaptation | Tick if it adresses climate adaptation considerably
Timeframe |  | Short | < 2 years | 1
|  | Medium | 2-5 years | 2
|  | Long | > 5 years | 3
Costs |  | Low | Within existing budgets | 1
|  | Medium | With small additional budgets | 2
|  | High | Needs significant dedicated external funds | 3
Feasibility | Assesment of the resources required, particular capacity and technical complexity | Very feasible | With current capacity and knowledge | 1
|  | Feasible | Manageable with some additional capacity and knowledge | 2
|  | Less feasibility | Complex - requires significant additional capacity and technical know-how | 3
Within WASAC mandate | Tick if it is clearly within WASAC mandate | Yes | Clearly within WASAC's mandate | 1
|  | Partial | Unclear or partially within WASAC's mandate | 2
|  | No | Clearly not within WASAC's mandate | 3
NDC | Is it included/part or Nationally Dertmined Contribution?
Existing processes/ strategies | Are there existing processes available, or is it a new initiative
Lead agency/ department/ line ministry | Please specify main lead
Other key partners
Adresses vulnerability | Link to vulnerability assesment - identify key vulnerability | Water quantity
Water quality
Resilient infrastructure
Reduce demand
Remarks

## Detailed reasoning
Strategy area | # | Activity Group | Reasoning
Strengthening ongoing NRW initiatives to reduce physical losses | 1.1 | Planning and executing improvements | WASAC’s NRW reduction and management plan (2018) should be revised, quantifying both commercial and physical components. In addition, the plan should identify short term “quick wins – activities that can be done immediately with less/no additional investment” and long-term interventions.
Strengthening ongoing NRW initiatives to reduce physical losses | 1.2 | Estimate current GHG emissions of WASAC and potential gains | Currently, the level of GHG emissions related to water supply and potential gains are unknown, which makes it difficult to design the necessary interventions. An assessment is, therefore, required which would also guide investment decisions.
Strengthening ongoing NRW initiatives to reduce physical losses | 1.3 | Identify existing schemes with high NRW related to climate hazards | Schemes with high NRW (especially physical losses) should be identified. This facilitates allocation of the scarce resources to improve and speed up pipe repair. In addition, measures should be designed to prevent pipeline damages that are instigated by climate change.
Strengthening ongoing NRW initiatives to reduce physical losses | 1.4 | Replacement of aged pipes (and any other network component) in selected schemes | The vulnerability assessment indicated that a number of pipelines are aged and some pipe components like float valves etc are nonfunctional, which contributes significantly to physical losses. The aged pipes and non-functional network components should be replaced to reduce physical losses.
Strengthening ongoing NRW initiatives to reduce physical losses | 1.5 | Network sectioning and introduction of SMART system monitoring | SMART technology can be useful in monitoring and, thereafter, reduce and manage NRW. The network should be sectioned according to set criteria which would ease monitoring of system flows and pressures.
Increasing energy efficiency by installing high efficient pumps and other energy saving technologies | 2.1 | Energy audit followed by replace all pumps with high energy efficient pumps | The first step is to do an energy audit – this leads to a quantification of the GHG emissions of WASAC and a quantification of the main energy intensive processes. Next, the asset inventory should be used to identify age, model and capacity of existing pumps. This should then lead by a scheduled replacement process over multiple years.
Increasing energy efficiency by installing high efficient pumps and other energy saving technologies | 2.2 | Replace all remaining diesel generator pumps with grid or solar | Diesel generators are both costly in operation and bad for the climate emissions. The number of these generators are quite low in Rwanda, and it is realistic to target to replace them during a 1–2-year programme, possibly with external funds.
Increasing energy efficiency by installing high efficient pumps and other energy saving technologies | 2.3 | Create organisation wide energy saving ethos and apply energy saving processes throughout production | Recognising that pumping is not the only energy consumption, the energy audit of 2.1. is anticipated to highlight other high energy intensive areas. This activity group should trigger energy saving and energy efficiency throughout WASAC’s operation. Main gains are expected in water treatment, but also more energy saving in trucking, construction and use of SMART meters.
Increasing energy efficiency by installing high efficient pumps and other energy saving technologies | 2.4 | Communication and awareness raising campaigns to reduce water demand and enhance community resilience | Reducing water demand leads to a reduction of energy needs, as less water needs to be treated and pumped. By building on existing communication processes, the end-users should be informed to reduce their water usages. Reduced demands also favourably influence the water resource management (Programme of Action).
Developing and implementing a risk-based asset management system. | 3.1 | Develop training material and train key colleagues | First steps in developing a risk-based asset management system have been made but only a limited number of staff has been involved. For further development it is crucial that key staff will be trained in the principles and methodologies of asset management.
Developing and implementing a risk-based asset management system. | 3.2 | Adapt asset categories to reflect risks | Asset categorization supports integration of risk-based thinking in asset management. The vulnerability assessment suggests four categories: Sources, Water Treatment Plant (WTP), Conveyance network and Service points. WASAC may adapt these categories in the risk-based asset management.
Developing and implementing a risk-based asset management system. | 3.3 | Improve performance monitoring of assets | Risk-based asset management includes the ability to assess the probability of asset failures. Therefore, it is important that the performance of the existing assets is monitored and reported, preferably in a central database. Point of attention is the reliability of the existing data. If unreliable, the database should be improved and cleaned up.
Developing and implementing a risk-based asset management system. | 3.4 | Develop a strategic infrastructure plan | The efforts and investments needed to arrive at a climate resilient infrastructure are huge and this cannot be achieved in one decade. It is recommended to develop a strategic infrastructure plan with a long plan horizon (e.g. 2050). This is not a blueprint but should be a high-over adaptive plan that gives direction to future investments, taking into account redundancy and resilience of infrastructure.
Adapting designs and norms to inclue climate change | 4.1 | Revise design norms and standards | The standards currently used by WASAC are conventional and don’t consider the climate change impact. They, therefore, should be revised because climate change significantly increased the likelihood of failure of the infrastructure leading to increased risk. Relevant agencies like the Rwanda Standards Board and the Ministry of Infrastructure should support WASAC in this activity. When the standards are developed, different (relevant) entities should be trained to utilize them.
Adapting designs and norms to inclue climate change | 4.2 | Identify infrastructure most at risk and their needed adaptation | The categorization of the assets in Strategic Area 3 should pave way for identification of the infrastructure most at risk, from the water source to the final water user. When identified, the needed adaptation measures should be designed and implemented.
Adapting designs and norms to inclue climate change | 4.3 | Enhanced supervision in areas that are more disaster prone | The vulnerability assessment identified regions/areas that are at high risks considering different climate hazard risks (drought, flooding and landslide). The supervision of infrastructure in the identified disaster-prone areas ought to be accordingly enhanced.
Reducing Water demand by using water saving devices | 5.1 | Engage with private sector to offer water saving devices to consumers | The main purpose will be to encourage the private sector to provide consumers with water-saving devices. The action plan should focus on the following actions: 1) Partnerships with manufacturers to increase the accessibility of water-saving devices for consumers such as water saving taps, toilets and showerheads; 2) Campaigns for education and awareness in partnership with the private sector on the advantage for utilizing water saving equipment’s; 3) Design incentives for customers to buy and use water saving devices which may also include product promotions.
Reducing Water demand by using water saving devices | 5.2 | Scale water component green city initiative | The focus for WASAC will be to support the green city initiatives by supporting cities administrators in a more efficient planning, management, billing and empowering households through water efficiency and cost saving measures. Such support should include: 1) Infrastructure projects that focus on sustainable water management 2) Encourage the adoption of water-saving devices in green cities 3) Rainwater harvesting 4) Implementation of climate resilient sanitation facilities 5) Regular monitoring and evaluation of the water and sanitation facilities in the green cities
Protecting priority assets (intake structures, pumping stations and conveyance pipes) against climate hazards | 6.1 | Based on (climate) vulnerability assessment create a detailed plan | The action plan should focus on the following options for building resilience of water and sanitation systems: 1) Protection measures for the water source(s); 2) Strengthening distribution and conveyance systems; 3) Protecting water and wastewater treatment plants; 4) Strengthening sanitation containment; 5) Other protection measures The detailed plan should appraise and prioritise options for adaptation.
Protecting priority assets (intake structures, pumping stations and conveyance pipes) against climate hazards | 6.2 | Implement detailed plan (e.g. shifting locations of intakes and pumping stations) | Based on the available resources the most priory options should be implemented e.g. shifting locations of intakes and pumping stations.
Protecting priority assets (intake structures, pumping stations and conveyance pipes) against climate hazards | 6.3 | All weather access to assets such as landfills, wastewater treatment plants | Roads to landfills and to wastewater treatment are not always tarmacked. They risk of being poorly accessible in bad weather, leading to reduced collection possibilities and lower hygienic circumstances.
Securing Sanitation and sewers to cope with floods and landslides | 7.1 | Avoid storm water entry into sewerage | Flooding of sewerage systems allows pathogens to come into the environment. This can be avoided by keeping rainwater and flood water out of sewerage system. For this drainages need to be made separately, both at household and building level, through to larger storm water designs
Securing Sanitation and sewers to cope with floods and landslides | 7.2 | Weatherproof latrines against extreme weather events | Latrines are owned by the households and through community awareness and campaigns, latrines should be promoted to be better weather proof. This can include stronger superstructures against strong winds, and design local water flows away from latrines and septic tanks.
Using real-time monitoring of weather and water resources data during extreme weather events | 8.1 | Create action protocol based on weather warnings | The main purpose will be to ensure the continued operation and safety of facilities during extreme weather events. The protocol should include activities such as: 1) Monitor weather alerts: Keep well-informed of weather predictions and advisories provided by Meteo-Rwanda and other relevant agencies; 2) Assess Possible Risks: Consider the possible harm that the weather forecast could do to water treatment system; 3) Call in the Emergency Response Team: in the event that a severe weather alert is issued that could have an impact on water treatment quality; 4) Protect the infrastructure: Take pro-active action to safeguard the infrastructure in case of extreme weather events.
Using real-time monitoring of weather and water resources data during extreme weather events | 8.2 | Monitor systems behaviour during extreme events | This could involve procedures for safely ending operations during intense events to avoid contamination or damage. Plans for evacuation should also be provided in case the situation gets out of control.
Using real-time monitoring of weather and water resources data during extreme weather events | 8.3 | Post- extreme event assessment | Following the extreme weather event, there is need to perform a comprehensive evaluation of any damage or effects to the water treatment infrastructure. This could involve putting in place the procedures for making the required fixes and enhancements to strengthen resilience against upcoming weather occurrences.
Implementing contingency plans for disasters | 9.1 | Define protocol on recording disaster events (via WASH Cluster) | The emergency WASH cluster is chaired by WASAC and co-chaired by UNICEF. Members include: MINEMA, MINALOC, MININFRA, MOH, RBC, REMA, RWB, TROCAIRE, Water for People, Alight, WVI and RRC. The protocol should focus on the following steps: 1) Compile Requirements from the stakeholders to identify the crucial information and data elements that must be kept such as location, disaster type, damage on WASH infrastructure, etc. 2) Define Data Collection Methods to gather data during disaster events (e.g. Standardized forms, online questionnaires, smartphone apps, etc.). 3) Determine Data Management Procedures for safely archiving, handling, and distributing the gathered data. 4) Pilot test and improve the protocol during actual or simulated disaster scenarios. 5) Continuously monitor how the protocol is being applied during emergency situations and assess how well it is accomplishing its goals.
Implementing contingency plans for disasters | 9.2 | Create financial mechanism for disaster recovery | The action plan should focus on putting in place procedures to finance and support post-disaster restoration. This should base on the developed vulnerability report (2024) which highlight various hazard and risk assessment and the WASAC group strategic plan. In addition, the financial mechanism should include other process such as: 1) Determine the potential funding sources, 2) Include risk financing techniques in the financial framework.
Implementing contingency plans for disasters | 9.3 | Create disaster management protocols at utility level | Disaster management protocols at the utility level are necessary to guarantee the continuation of vital services including water and sanitation services delivery during and after disasters. This should base on the existing emergency response protocols at MINEMA.
Implementing contingency plans for disasters | 9.4 | Create redundancy in sources and systems | This activity will propose a range of measures in building redundancy in water sources and systems such as to determine and create a variety of water sources, including surface water reservoirs and groundwater wells, decentralised water supply systems, etc. resilient climate infrastructure design.
Strengthening ongoing NRW initiatives to reduce physical losses | 10.1 | Hire and train stakeholder managers | Catchment protection is important for creating a more resilient water and sanitation infrastructure. To influence decision making and to make sure the right protection programmes and projects are initiated it is important hire stakeholder managers. Stakeholder managers are important for: - Communication and stakeholder engagement; - Sustaining effective working relations with other stakeholders to ensure project objectives are achieved; - Identifying, advising and prioritising catchment protection programmes and projects; - Jointly develop proposals for funding of projects and programmes; - Ensure project/programme activities are aligned with organisational strategy; - Use influence and authority to assist the programme/project in achieving its outcomes.
Strengthening ongoing NRW initiatives to reduce physical losses | 10.2 | Formulate and implement a company-wide stakeholder management vision and strategy | Describe the current issue/problem and explain why stakeholder management is important. Set the boundaries of the playing field where stakeholder managers can operate.
Strengthening ongoing NRW initiatives to reduce physical losses | 10.3 | Strengthen the existing catchment management committees and participate in water resource allocation | A multi-stakeholder approach is essential for developing and implementing joint plans for Integrated Water Resources Management (IWRM). Catchment management committees if existing should be strengthened and become more mature. WASAC and the drinking water sector at large should have a strong presence in these committees. A mature catchment management committee should have: - High profile support and commitment at national and regional government levels; - Institutionalised platform and process for stakeholder participation and collaboration; - Clear vision, mandates and responsibilities; - Joint catchment protection workplans and budget for prioritised projects and activities; - Systematic and improved knowledge management. Building on best practices and lessons learned; - Commitment and passion among partners.
Strengthening ongoing NRW initiatives to reduce physical losses | 10.4 | In high turbidity areas enhance riverbed protection and erosion measurements | With the water catchment authorities, prioritise the catchments that have high turbidity and promote riverbed protection and erosion measurements
Strengthening ongoing NRW initiatives to reduce physical losses | 11.1 | Assemble water safety plan teams and describe the water supply systems | There ought to be a team to champion the development and implementation of the water safety plan. When established, the team should commence with description of the water supply systems as the first step.
Strengthening ongoing NRW initiatives to reduce physical losses | 11.2 | Hazard and risk assessment | System hazards and hazardous events should be identified in an assessment conducted by the water safety planning team. At this stage, the risks should also be categorised and prioritized.
Strengthening ongoing NRW initiatives to reduce physical losses | 11.3 | Planning and executing improvements | The prioritized risks will lead to development of an improvement plan consisting of control measures that should be executed and maintained.
Strengthening ongoing NRW initiatives to reduce physical losses | 11.4 | Monitoring for control measures | The defined control measures ought to be monitored so that the effectiveness of the water safety plan is verified.
Strengthening ongoing NRW initiatives to reduce physical losses | 11.5 | Periodic review of the water safety plan | The water safety plan should be kept live i.e., reviewed and updated regularly. This is because there could be new risks, or it could be that some of the already identified risks have changed, for example from high to moderate or low.
Strengthening ongoing NRW initiatives to reduce physical losses | 12.1 | Analysis of trends in water resources availability for critical intake points | Identify the areas and systems most at risk for drought. This is largely in the East. In these areas, identify the most critical systems using risk assessments, serving larger number of people and set up a monitoring system. Install weirs and other yield monitoring equipment and set-up a section withing WASAC to combine water source data with larger meteo and climate trends.
Strengthening ongoing NRW initiatives to reduce physical losses | 12.2 | Create national spring monitor system | Conduct inventory of springs in the country, with initial focus on those that are used for drinking water, but eventually with all other springs. Set-up system to capture yields, at least twice a year (dry and rainy season)
Strengthening ongoing NRW initiatives to reduce physical losses | 13.1 | Risk categorisation of rural water infrastructures, also in design phase | Based on the vulnerability report, this should include identifying and classifying potential risks and vulnerabilities associated with rural water infrastructures starting from the design phase. This should be followed by developing mitigation strategies for targeted risks.
Strengthening ongoing NRW initiatives to reduce physical losses | 13.2 | Enhance protection zones around springs and boreholes in water catchment areas | Enhanced protection should focus in water catchment areas where springs and boreholes are located. The long-term sustainability of this activity will also require to implement Land Use Planning and enhance community participation through the existing water catchment committees.
Strengthening ongoing NRW initiatives to reduce physical losses | 13.3 | Explore alternative options such as water kiosks | For communities to obtain safe drinking water, water kiosks can serve as decentralized locations. In some areas water can be drawn from adjacent boreholes, springs, or piped water systems.
Strengthening ongoing NRW initiatives to reduce physical losses | 13.4 | Communication and awareness raising campaigns to enhance community resilience | Through education, engagement, and empowerment, these campaigns should aim to help communities embrace behaviours and practices that support water safety, sanitation, and hygiene as well as to adapt to climate change impact.